## ziongallery
ZionGallery
Planning
Name | Subitems | Owner | Priority | Status | Timeline - Start | Timeline - End
Project Proposal |  |  | High | Done | 2020-09-06 | 2020-09-06
Use Cases and Requirements |  |  | High | Done | 2020-09-26 | 2020-09-26
Tool Selection Review |  |  | High | Done | 2020-09-28 | 2020-09-28
Project Review |  |  | High | Done | 2020-10-01 | 2020-10-01
Software Project Management Plan (SPMP) |  |  | Critical | Done | 2020-10-02 | 2020-10-02
[5 empty] | 2020-09-06 | 2020-10-02
Designing
Name | Subitems | Owner | Priority | Status | Timeline - Start | Timeline - End
Meeting with the professor |  |  | Critical | Done | 2020-10-07 | 2020-10-07
Gather Paintings | Talk with the client |  | High | Done | 2020-10-07 | 2020-10-11
Subitems | Name | Owner | Status | Date
| Talk with the client |  | Done | 2020-10-08
Design the website (High level) |  |  | High | Done | 2020-10-13 | 2020-10-13
Hostgator and wordpress | get the host and domain from hostgator.com |  | Critical | Done | 2020-10-15 | 2020-10-15
Subitems | Name | Owner | Status | Date
| get the host and domain from hostgator.com |  | Done | 2020-10-15
[5 empty] | 2020-10-07 | 2020-10-15
Developing
Name | Subitems | Owner | Priority | Status | Timeline - Start | Timeline - End
work on Homepage |  |  | High | Done | 2020-10-15 | 2020-10-18
work on about us page |  |  | High | Done | 2020-10-17 | 2020-10-20
work on contact us page |  |  | High | Done | 2020-10-20 | 2020-10-20
work on paintings page |  |  | Critical | Done | 2020-10-21 | 2020-10-25
wonk on payment options |  |  | Critical | Done | 2020-10-29 | 2020-11-02
work on Reviews page |  |  | Medium | Done | 2020-11-03 | 2020-11-05
[5 empty] | 2020-10-15 | 2020-11-05
Testing and Launching
Name | Subitems | Owner | Priority | Status | Timeline - Start | Timeline - End
Update the website |  |  | Medium | Done | 2020-11-06 | 2020-11-06
pre-testing on each functions and pages |  |  | High | Done | 2020-11-03 | 2020-11-05
Fixing issues |  |  | Critical | Done | 2020-11-10 | 2020-11-13
Testing |  |  | High | Done | 2020-11-17 | 2020-11-18
Presentation |  |  | Critical | Working on it | 2020-12-01 | 2020-12-01
[5 empty] | 2020-11-03 | 2020-12-01